AKBai

Operations Infrastructure Roadmap

Kaakbay mo sa negosyo.

Internal Planning Document · Confidential

v1.0 · March 2026

Prepared by: Anton del Rosario

Companion Document: AKBai Complete Roadmap v8.0

CONFIDENTIAL — For Internal Planning Only

# Why a Separate Operations Roadmap

The product roadmap covers what users see and interact with — the PWA, chat interface, dashboards, BIR features. The operations roadmap covers what Anton sees and manages: the internal infrastructure that keeps AKBai running reliably, scales with the user base, and keeps Anton sane as a solo founder. These are distinct codebases, tools, and workflows that must be planned separately to avoid scope creep in the product build.

## Four Operations Domains

| Domain | What It Is |
| --- | --- |
| Admin Dashboard | Internal tool for Anton to manage users, subscriptions, flags, and observe system health |
| Billing Pipeline | Xendit webhook handling, subscription state machine, grace periods, plan enforcement |
| Support Infrastructure | WhatsApp Business API setup, response templates, triage and escalation workflows (M1-M6: personal WhatsApp with AKBai business name, M7+: WhatsApp Business API) |
| Monitoring & Alerting Stack | Sentry, UptimeRobot, PostHog, health check endpoints for all 4 external APIs |

## Ops vs Product — Key Principle

The product roadmap builds what users pay for. The ops roadmap builds what lets Anton sleep at night. Both are required. Neither is optional.

# OPS Build 0 — Monitoring & Alerting Foundation

OPS BUILD 0 ¦ Must ship before any beta user onboards ¦ ~8 hours ¦ Phase 0A D97706

## Why This Ships First

Without monitoring you are blind. If the Claude API goes down during a BIR deadline, you will not know until a user WhatsApps you in a panic. This build creates visibility into every layer of the stack before a single real user touches the product.

## Tools & Setup

| Tool | Purpose | Cost | Setup Priority |
| --- | --- | --- | --- |
| Sentry | JavaScript error tracking, crash reports, source maps | $0–$26/mo | CRITICAL — Day 1 |
| UptimeRobot | HTTP uptime monitoring for all API endpoints + PWA | $7/mo Pro | CRITICAL — Day 1 |
| PostHog | Product analytics, user funnels, Sense Check Gate signals | $0 (free up to 1M events) | CRITICAL — Day 1 |
| Supabase Dashboard | Built-in DB metrics, query performance, RLS audit | Included in Pro | CRITICAL — Day 1 |
| Better Uptime (optional) | Public status page + on-call push alerts | $0–$20/mo | NICE TO HAVE |

## Health Check Endpoints

Create a /api/health endpoint in Next.js that pings all 4 external dependencies and returns a status JSON. UptimeRobot monitors this every 5 minutes. If any dependency fails, Anton gets a push notification within 5 minutes.

| Dependency | Check Method | Failure Action |
| --- | --- | --- |
| Supabase | SELECT 1 query | Show 'service degraded' banner in app |
| Claude API (Anthropic) | Lightweight ping with 10-token prompt | Fall back to static FAQ responses, show AI unavailable banner |
| Claude Haiku Vision | Receipt scan test (lightweight) | Disable receipt scanning, show manual entry prompt (Pro: 30/month, Business: 60/month, Free: 0 scans) |
| Xendit | Webhook endpoint health | Pause subscription billing, log for manual retry |

## Anton's Alert Protocol

- UptimeRobot detects downtime → Push notification to Anton's phone within 5 minutes

- Anton checks /api/health endpoint to identify which dependency failed

- Check dependency status page (status.anthropic.com, status.supabase.com, etc.)

- Post in-app banner: 'Ang AKBai ay may technical issue ngayon. Bumabalik kami agad.' (Taglish)

- Resolve or escalate per OPS Flow 2 Incident Runbook (see Operations Playbook)

## Effort Estimate

| Task | Hours |
| --- | --- |
| Sentry integration + source maps | 2h |
| UptimeRobot setup + /api/health endpoint | 2h |
| PostHog integration + event taxonomy | 3h |
| Alert protocol documentation | 1h |
| Total | 8 hours |

# OPS Build 1 — Billing Pipeline

OPS BUILD 1 ¦ Xendit integration + subscription state machine ¦ ~14 hours ¦ Phase 1 — Build 4 D97706

## Why This Is Separate from the Product Build

The product build handles what users see when they upgrade (the UI, the paywall, the upgrade CTA). The billing pipeline handles what happens behind the scenes: webhook receipt, idempotency checks, subscription state transitions, grace periods, and plan enforcement at the API layer. Getting this wrong means double-charging users or failing to cut off expired subscriptions — both are catastrophic for a solo founder's reputation.

## Subscription State Machine

| State | Trigger | What Happens |
| --- | --- | --- |
| FREE | New signup | Free tier active, 10 queries/day limit enforced (Haiku-only routing) |
| ACTIVE | Xendit payment.succeeded webhook | Pro/Business features unlocked, limit removed |
| GRACE | Xendit payment.failed webhook | Pro features retained for 3 days, daily push reminder sent |
| EXPIRED | Grace period ends (72h cron) | Downgraded to Free tier, data preserved, upgrade prompt shown |
| CANCELLED | User cancels | Active until end of billing period, then FREE |
| REFUNDED | Xendit refund processed | Immediate downgrade to TRIAL |

## Webhook Idempotency (Critical)

Xendit webhooks can fire multiple times for the same event (network retry on timeout). The handler MUST deduplicate by payment_id before processing any state transition. Use a webhook_events table in Supabase with a unique constraint on (payment_id, event_type). If the row already exists, return 200 OK immediately without processing.

## Grace Period Cron

A Supabase Edge Function runs every 6 hours. It queries all subscriptions in GRACE state where grace_started_at is older than 72 hours. For each expired subscription: set state to EXPIRED, send final push notification, enforce Free tier limits immediately.

## Plan Enforcement Architecture

Plan enforcement happens at the API middleware layer, not in the UI. Every AI query checks the user's current subscription state from Supabase before processing. This prevents tier bypass via direct API calls. The check adds ~5ms latency.

## Effort Estimate

| Task | Hours |
| --- | --- |
| Xendit webhook handler + idempotency table | 3h |
| Subscription state machine (Supabase schema + transitions) | 3h |
| Grace period cron (Edge Function) | 2h |
| Plan enforcement middleware | 2h |
| Xendit test mode integration testing | 2h |
| Billing event logging + admin visibility | 2h |
| Total | 14 hours |

# OPS Build 2 — Admin Dashboard

OPS BUILD 2 ¦ Internal visibility + control panel for Anton ¦ ~18 hours ¦ Phase 1 — Post-launch (Month 2) D97706

## Philosophy

The admin dashboard is not a product feature. It is Anton's cockpit. For 0–200 users it can be a combination of Supabase Studio + a simple Retool view. Do not over-engineer this — the goal is visibility and control, not beauty.

## Dashboard Modules

| Module | What Anton Sees | Build Approach | Status |
| --- | --- | --- | --- |
| User Overview | Total users, active today/week/month, new signups, churn | Supabase view + PostHog dashboard | Phase 1 |
| MRR & Revenue | MRR breakdown by plan (Beta/Free/Pro/Business), MRR growth, Xendit reconciliation. Reference: Financial Model v2. | Supabase query + Xendit dashboard | Phase 1 |
| Feature Usage | Most-used features, Kilala Kita completion rate, bootstrap path breakdown | PostHog funnels | Phase 1 |
| Flag-as-Wrong Queue | All AI responses flagged by users, raw content, response correction needed | Custom Supabase table + Retool view | Phase 1 |
| Subscription States | Count by state (TRIAL/ACTIVE/GRACE/EXPIRED), at-risk accounts | Supabase view | Phase 1 |
| API Health | Current status of all 4 dependencies, last check time | /api/health endpoint | Phase 0A |

## Feature Flags via Supabase

Store feature flags in a Supabase config table (key, value, description, updated_at). The product reads these on each session. Anton can toggle features on/off for all users or specific user groups without a code deploy. Example flags: bir_features_enabled, voice_input_enabled, google_sheets_beta.

| Flag | Default | Purpose |
| --- | --- | --- |
| bir_features_enabled | true | Master switch for all BIR features |
| data_bootstrap_csv | true | Enable CSV/XLSX upload path in Kilala Kita |
| voice_input_beta | false | Enable Whisper voice input for beta users |
| google_sheets_oauth | false | Enable Google Sheets OAuth (Phase 2) |
| maintenance_mode | false | Show maintenance banner to all users |

## Effort Estimate

| Task | Hours |
| --- | --- |
| Supabase views for user + revenue metrics | 4h |
| PostHog dashboard configuration | 2h |
| Feature flags config table + product integration | 4h |
| Flag-as-Wrong queue + Retool view | 4h |
| Subscription state overview query | 2h |
| Basic admin auth (separate Supabase role) | 2h |
| Total | 18 hours |

# OPS Build 3 — Support Infrastructure

OPS BUILD 3 ¦ WhatsApp Business API + triage system ¦ ~10 hours ¦ Phase 1 — 2 weeks before launch 0B7A6E

## Support Channel Decision

Support runs through WhatsApp Business (primary) and Viber (secondary). Both are widely used in the Philippine MSME market. Email support is available but deprioritized — most target users prefer messaging over email. A formal ticketing system (Zendesk, Freshdesk) is overkill for 0–200 users; a structured WhatsApp workflow with a Notion triage log is sufficient.

## WhatsApp Business Setup

| Item | What To Do | Priority |
| --- | --- | --- |
| Business account | Register AKBai WhatsApp Business account (Meta Business Suite) | CRITICAL |
| Display name | 'AKBai Support' with AKBai logo | CRITICAL |
| Business hours | Set: Mon–Fri 8AM–8PM PHT (Solo founder hours) | CRITICAL |
| Auto-reply | Set welcome message + expected response time in Taglish | CRITICAL |
| Quick replies | Create 10 template responses for most common issues | IMPORTANT |

## Response Templates (Taglish)

| Scenario | Template |
| --- | --- |
| General greeting | 'Kamusta! Ito si AKBai Support. Paano kita matutulungan ngayon?' |
| Acknowledge receipt | 'Salamat sa iyong mensahe! Nakuha na namin ito. Susugurin namin sa loob ng 4 na oras.' |
| Bug report ack | 'Naiintindihan namin ang issue mo. Nag-log na kami nito at inaayos na. Aabisuhan ka namin pagkatapos.' |
| Feature request | 'Salamat sa suggestion! Idinagdag na namin ito sa aming feature backlog.' |
| BIR question | 'Para sa specific tax advice, kumonsulta sa isang CPA. AKBai ay nagbibigay ng general guidance lamang.' |
| Resolved | 'Naayos na ang iyong issue. Pakitingnan at i-update mo kami kung may iba pang nararamdaman.' |

## Triage Protocol

| Priority | Definition | Response Target | Example |
| --- | --- | --- | --- |
| P0 — Critical | App down, data loss, payment issue | 1 hour (any time) | 'AKBai won't load' |
| P1 — High | Feature broken, user cannot complete core task | 4 hours (biz hours) | 'BIR deadline not showing' |
| P2 — Medium | Unexpected behavior, confusion, minor bug | 24 hours (biz hours) | 'Button alignment weird' |
| P3 — Low | Feature request, general feedback, how-to question | 48 hours (biz hours) | 'Can you add X feature?' |

## Effort Estimate

| Task | Hours |
| --- | --- |
| WhatsApp Business account setup + verification | 2h |
| Auto-reply + template messages setup | 2h |
| Notion triage log template creation | 1h |
| Response template library (10 templates) | 2h |
| Viber Business account setup | 1h |
| Support SLA documentation for website/app | 2h |
| Total | 10 hours |

# OPS Build 4 — BIR Calendar Management

OPS BUILD 4 ¦ BIR deadline data pipeline ¦ ~6 hours ¦ Phase 1 — Build 3 dependency 7D3C98

## Why BIR Calendar Is an Operations Problem

BIR deadlines change every year. The TRAIN Law and subsequent revenue regulations regularly adjust filing dates, add new deadlines, and modify form requirements. If the bir_deadlines table in Supabase has wrong dates, AKBai sends wrong alerts — which is legally and reputationally damaging. BIR calendar management must be treated as an ongoing operational responsibility, not a one-time data entry task.

## Calendar Data Architecture

| Column | Type | Description | Example |
| --- | --- | --- | --- |
| id | UUID | Primary key | uuid |
| deadline_type | TEXT | Type of BIR filing | quarterly_income_tax |
| form_number | TEXT | BIR form reference | 1701Q |
| due_date | DATE | Filing/payment deadline | 2026-05-15 |
| bir_type_applicable | TEXT[] | Array: 8pct, graduated, or both | {8pct, graduated} |
| notes | TEXT | Any special conditions | Extended due to Eid al-Fitr |
| updated_at | TIMESTAMP | Last admin update | 2026-01-15 09:00:00 |
| source_url | TEXT | BIR RMC/circular ref | https://bir.gov.ph/... |

## Annual Calendar Refresh Workflow

- January: Monitor BIR website and official gazette for new Revenue Memorandum Circulars (RMCs)

- Cross-reference with previous year's calendar — identify changes

- Update bir_deadlines table in Supabase admin UI (no code deploy needed)

- Run a query to verify all deadlines have source_url populated

- Test that push notifications fire correctly for the updated dates in staging

- Confirm at least 2 weeks before first Q1 deadline of the year

## BIR Deadline Categories to Track

| Category | Key Deadlines |
| --- | --- |
| Percentage Tax (Non-VAT) | Monthly: Form 2551M (20th of following month) |
| Income Tax (8% flat) | Quarterly: Form 1701Q (May 15, Aug 15, Nov 15); Annual: Form 1701A (Apr 15) |
| Income Tax (Graduated) | Quarterly: Form 1701Q same dates; Annual: Form 1701 (Apr 15) |
| VAT | Monthly: Form 2550M (20th); Quarterly: Form 2550Q (25th after quarter) |
| Withholding Tax | Monthly: Form 0619-E / 1601-EQ |
| Registration | Annual: Form 0605 (Jan 31) |

## Effort Estimate

| Task | Hours |
| --- | --- |
| bir_deadlines table schema + RLS policies | 2h |
| Admin update UI (simple Supabase form) | 2h |
| Annual refresh workflow documentation | 1h |
| First year calendar data entry (2026) | 1h |
| Total | 6 hours |

Infrastructure Cost-Trigger Milestones (not calendar-based):

Hosting (Vercel → Cloudflare Pages): M1–M6 ₱0 → Month 7 ₱286 ($5)

Database (Supabase free → Pro): M1–M9 ₱0 → Month 10 ₱1,430 ($25)

WhatsApp Business API: M1–M6 ₱0 → Month 7 ₱572 ($10)

Monitoring (PostHog/Sentry free): All Y1–Y3 ₱0

NPC (National Privacy Commission) Registration: Pre-launch CapEx ₱10,000 (legal/registration)

Business Tier Launch: Phase 2 / Month 13 (₱799 Y1 → ₱899 Y2 → ₱999 Y3, with 60 receipt scans/month)

Pro Tier Pricing: ₱299 Y1 → ₱349 Y2 → ₱399 Y3 (30 receipt scans/month)

Unit Economics: Pro LTV ₱7,475 · Blended CAC ₱110 · LTV/CAC ratio 68x · Payback period 0.4 months (12 days)

NPC Registration: Required pre-launch before Phase 1 public launch (hard gate during Phase 0C pilot)

# Operations Roadmap — Timeline

| OPS Build | Name | Phase | Effort | Dependency |
| --- | --- | --- | --- | --- |
| OPS Build 0 | Monitoring & Alerting Foundation | Phase 0A — Week 1-2 | 8h | None — ships first |
| OPS Build 1 | Billing Pipeline | Phase 1 — Weeks 6-7 | 14h | Product Build 4 |
| OPS Build 2 | Admin Dashboard | Phase 1 — Weeks 9-10 | 18h | OPS Build 1 |
| OPS Build 3 | Support Infrastructure | Phase 1 — 2 wks before | 10h | None (parallel) |
| OPS Build 4 | BIR Calendar Mgmt | Phase 1 — Week 5 | 6h | Product Build 3 |
| TOTAL | All Ops Builds | Phase 0A–Phase 1 | 56h | — |

## Ops Build Dependencies on Product Builds

| Ops Build | Depends On | Why |
| --- | --- | --- |
| OPS Build 1 (Billing) | Product Build 4 | Cannot build billing pipeline without subscription UI/schema in product |
| OPS Build 2 (Admin) | OPS Build 1 + PostHog | Admin dashboard is meaningless without billing data and analytics |
| OPS Build 4 (BIR Calendar) | Product Build 3 | BIR deadline table must align with the BIR features schema |

This is a hard gate before Phase 1 public launch. UAT testers are not charged — they receive free access in exchange for structured feedback on core flows (Kilala Kita, Receipt Scanner, Dashboard, Morning Briefing).

UAT Cost: ₱800 total (Claude Haiku API for 15 testers × 4 weeks)

Monitoring: PostHog free only

WhatsApp Business API: NOT active

Payments: NOT active (no Xendit, no billing)

Analytics: PostHog free tier

Email: Resend free tier

Hosting: Cloudflare Pages free tier

Database: Supabase free tier

Claude API: Haiku only (no Sonnet) — testers can use the AI assistant

UAT Stack (stripped-down):

Before any public-facing launch, a User Acceptance Testing (UAT) environment runs for 2–4 weeks with 15–20 invited testers.

OPS Build UAT — Pre-Launch Testing Environment

## Phase 2+ Operations Roadmap

After the Sense Check Gate passes (target: after Month 12, when AKBai reaches ~400 users and ₱63,773 cumulative net profit per Y1 projections), operations infrastructure should be extended to support growth. Key Phase 2 ops items include:

- OPS Build 5: Automated user onboarding email sequences (PostHog + SendGrid/Resend)

- OPS Build 6: Referral tracking pipeline (referral_codes table + conversion attribution)

- OPS Build 7: Advanced admin dashboard with cohort analysis and churn prediction signals

- OPS Build 8: Multi-agent support bot (AI-assisted first-response to common support tickets)

# Ops Roadmap Summary

| Metric | Value |
| --- | --- |
| Total ops build effort (Phase 0A → Phase 1 launch) | 56 hours |
| Runs parallel to product builds? | Yes — ops are separate, can work concurrently |
| Solo founder feasibility | Yes — each build is self-contained 1–3 day sprints |
| Phase 2 ops additions planned | 4 more builds identified (OPS Builds 5–8) |
| Companion documents | AKBai_Complete_Roadmap_v8.pdf (product), AKBai_Operations_Playbook.pdf (process flows) |

This Operations Roadmap is a DRAFT for Anton's review. Once confirmed, the ops builds will be incorporated into the main AKBai Complete Roadmap as a dedicated Ops Roadmap section alongside the product phases.